## Slide 1: Managed camps Update

## Slide 2: Overall approach
Finalize camp Locations
County identified land for affordable housing
Identify Land RV Parks
Today
Expedite
Fast Track
Medium Term
September
December
RFP for Manager
Open first camp
Open second camp
November
October
RFP selection
Renovations at Division St Shelter
Begin entitlement on Camp Sites
RFP for RV park
RFP for Navigation Center
Open the Navigation Center
Close on 2nd St
Renovations at 2nd St Shelter
Development Code Changes & Identify Land for Safe Parking

## Slide 3: Sanctioned encampment Site Characteristics
Site Priorities for Operators
15-25 sites/campers
Perimeter markings
Access to water
Circulation, space for Medical van
Estimated $300K-$400K annually
Proximity to social services, transit, employment etc
Essential Site Characteristics
Undeveloped
Publically owned
Existing street access
Existing water service
Street Address (or ability to get one)
Ability (with entitlement work) to approve permanent transitional housing/shelter

## Slide 4: Site #1 | 9th Street

## Slide 5: Site #1 | 9th Street
Agreement from Council to proceed
Begin conversations with adjacent neighbors
  Followed by open public meetings
Site visit with Parks
Overall site plan and approval under HB 2006
Open RFP for service provider to manage camp
Overall agreement on site plan for future permanent structures

## Slide 6: Site #2 | SE 3rd Street

## Slide 7: Site #2 | SE 3rd Street
Agreement from Council to proceed
Begin conversations with adjacent neighbors
  Followed by open public meetings
Contingent on successful negotiation of agreement with ODOT
Overall site plan and approval under HB 2006
Open RFP for service provider to manage camp
Overall agreement on site plan for future permanent structures

## Slide 8
Photo credit: Stories of Us: Camp Second Chance, Melinda Raebyne